## Summary
PROPOSAL SUMMARY
Client Name | Mattel
Project Name | AG
Total Estimated Effort (hrs) | 3417
Effort saved due to Sirius Assets | 3.889%
Total Costs($) | 135302.4
Cost saved due to Sirius Offshore | 67.21%
Estimated Start Date | 2017-02-01
Estimated End Date | 2017-08-02

## Estimator
Business Domain | Retail
Users | Customers
Type of App | Products Catalog
Operating System | Web | 20
| iOS | 8
| Android | 12
Team Distribution | All offshore
Screen Complexity
Complexity | No of Screens | Effort Factor
Simple | 3 | 1
Complex | 2 | 1.6
No of Widgets Used
Complexity | No of Screens | Effort Factor
Complex | 4 | 1.6
Native Features
Complexity | No of Screens | Effort Factor
Medium | 6 | 1.2
User Management
Integration | Complexity | Effort Factor
Facebook |  | 1
Security Requirements | SSL | 1.2
External API Integration
Type of Integration | Technology Used | No of Integrations | Effort Factor
External - Public | REST | 1 | 1.2
Domain Specific Use cases
Use Case | Complexity | Effort Factor
Buy Policy | Medium | 1.2
Custom Features & Functionalities
IBM Connections App |  | 80 | 112
BlueMix Services integration |  | 16 | 22.4
QR Code Scanner |  | 24 | 36
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Development Effort | Web | 588
| iOS | 307.2
| Android | 400.8
Total Development Effort |  | 1296
Effort Saved due to Sirius Assets |  | 50.4
% of Effort saved |  | 3.889%

## Effort Estimates
Task | Effort(Hrs)
Architecture Effort | 336.96
Design Effort | 336.96
PM Effort | 336.96
Development Effort - based on Project Type | 1296
Testing Effort | 673.92
QA Testing Support - Developers | 168.48
UAT Testing | 64.8
UAT Support - Developers | 84.24
UAT Support - Testers | 84.24
Production & Post Production Support | 33.696
Total Estimate | 3417

## Sprint Calculator (hidden)
Total Effort | 3417 | Sprint Durations (in weeks) | 2
|  | Number of Developers | 1
|  | Number of Sprints | 42.7125
PM Resources | 336.96
Architect Resources | 336.96
Testing Resources | 673.92
Creative Resources | 336.96

## Resource Plan (hidden)
Gantt Chart |  | Elaboration | Construction | Transition
Inception
Elaboration
Construction
Iteration 1
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Transition
Production
Resource Plan |  |  |  |  | Totals
|  | Inception | Inception | Inception
Resource Role |  | 2016-02-01 | 2016-02-08 | 2016-02-15 | Inception | Elaboration | Construction | Transition | Production | Total
BA-CR-UX1 | Business Analyst |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DA1 | Domain Architect |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PM1 | Project Manager |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCDV1 | Developer - Delivery Centre |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCDV2 | Developer - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCUI1 | UI Developer - Onshore - Delivery Centre |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
QAL1 | QA Lead |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSQA1 | Functional Tester - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
INFS1 | Dev Lead - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DD1 | Delivery Executive |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCCR1 | Delivery Centre - Coordinator |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSQAL1 | QA Lead - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
UX Architect | User Experience Architect |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Creative | Creative Designer |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Infrastructure Specialist |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HOURS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Totals from Resource Plan
Comparison to Estimates |  |  |  |  | Inception | Elaboration | Construction | Transition | Production | Total
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Construction = [Elaboration]+7
Note on C15: Enter project start date

## Cost Estimates
Resources | Onsite Effort(hrs) | Offshore Effort(hrs) | Onsite Cost($) | Offshore Cost($) | Cost if developed at Onsite | Cost Saved due to Offshoring
Architects | 0 | 336.96 | 0 | 13478.4 | 40435.2 | 66.67%
Designers | 0 | 336.96 | 0 | 13478.4 | 40435.2 | 66.67%
Project Managers | 0 | 336.96 | 0 | 13478.4 | 47174.4 | 71.43%
Developers | 0 | 1296 | 0 | 51840 | 155520 | 66.67%
QA testers | 0 | 673.92 | 0 | 26956.8 | 80870.4 | 66.67%
QA Support - Developers | 0 | 168.48 | 0 | 6739.2 | 20217.6 | 66.67%
UAT Support - Developers | 0 | 64.8 | 0 | 2592 | 7776 | 66.67%
UAT Support - Testers | 0 | 84.24 | 0 | 3369.6 | 10108.8 | 66.67%
Production & Post Production Support | 0 | 84.24 | 0 | 3369.6 | 10108.8 | 66.67%
Total | 0 | 3382.56 | 0 | 135302.4 | 412646.4 | 67.21%
|  | Total Costs | 135302.4
|  | Cost Saved due to Sirius Offshore | 67.21%
Note on A1: Microsoft Office User: Does'nt include UAT since UAT will be done by Clients

## Plan
RESOURCE PLAN
Total Effort | 3417 | hours
Sprint Duration | 4 | weeks
No of developers | 3 | resources
No of testers | 3 | resources
No of UAT Testers | 1 | resources
SPRINT PLAN
Design Schedule | 6 | weeks
Development Schedule | 11 | weeks
Testing Schedule | 6 | weeks
UAT Schedule | 2 | weeks
Production Schedule | 1 | weeks
Total Schedule | 26 | weeks
Total no of sprints | 7 | sprints
SCHEDULE PLAN
Estimated Start Date | 2017-02-01
Estimated End Date | 2017-08-02
EFFORT PLAN
| Week No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
| Week Starting on | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2017-03-01 | 2017-03-08 | 2017-03-15 | 2017-03-22 | 2017-03-29 | 2017-04-05 | 2017-04-12 | 2017-04-19 | 2017-04-26 | 2017-05-03 | 2017-05-10 | 2017-05-17 | 2017-05-24 | 2017-05-31 | 2017-06-07 | 2017-06-14 | 2017-06-21 | 2017-06-28 | 2017-07-05 | 2017-07-12 | 2017-07-19 | 2017-07-26
Architecture & Design Sprint |  | 120 | 120 | 120 | 120 | 120 | 73.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Testing Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 120 | 120 | 120 | 73.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Support Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.08 | 28.08 | 28.08 | 28.08 | 28.08 | 28.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 24.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Support - Testers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.12 | 42.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Support - Developers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.12 | 42.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production & Post Production Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.696 | 0 | 0 | 0 | 0 | 0 | 0

## Lookup
Business Domain | Users | App Functionality | App OS | Security Requirements | Application Type | Technology Used | User Management | Base Effort |  | Screen Complexity |  | No of Widgets |  | Native Features |  | User Management |  | External API |  | Insurance Specific Use cases |  |  | Application Type | Integration | Param | Factor | Security Requirements | Factor
Retail | Agents/Brokers | Products Catalog | iOS | SSL | Internal | SOAP | Google | iOS | 8 | Simple | 1 | Simple | 1 | Simple | 1 | Google | 1 | SOAP | 1.6 | Buy Policy | Medium | 1.2 | Internal | SOAP | InternalSOAP | 1 | SSL | 1.2
Healthcare | Sales | Account Management | Android | Integration with ISAM | External - Public | REST | LinkedIn | Android | 12 | Medium | 1.2 | Medium | 1.2 | Medium | 1.2 | LinkedIn | 1 | REST | 1.4 | Pay Policy | Complex | 1.4 | Internal | REST | InternalREST | 1.1 | Integration with ISAM | 1.3
Life Insurance | Customers | Payment | Windows | 2-Factor Authentication | External - Custom |  | Facebook | Windows | 16 | Complex | 1.6 | Complex | 1.6 | Complex | 1.6 | Facebook | 1 |  |  | Create Claim | Medium | 1.2 | External - Public | SOAP | External - PublicSOAP | 1.1 | 2-Factor Authentication | 1.5
Auto Insurance | Providers | Customer Service | Web | Custom Data Encryption |  |  | LDAP | Web | 20 | [6 empty] | LDAP | 1.2 |  |  | View Claim Status | Simple | 1.1 | External - Public | REST | External - PublicREST | 1.2 | Custom Data Encryption | 1.6
Banking | Underwriters | E-Commerce | [20 empty] | External - Custom | SOAP | External - CustomSOAP | 1.2
Electrical Components | Claim Specialists | [21 empty] | External - Custom | REST | External - CustomREST | 1.3
Manufacturing & Logistics
Utilities

## Guidelines
Environment Setup (Applicable for Hybrid) | Estimation(Minimum) | Buttons | Form fields | Validations | UI Widgets | Static Data | Dynamic Data | Gestures | Animations
Simple Screen |  | 1 | 4 | No | No | Yes |  | No | No
Medium Screen |  | 2 | 6 | yes | No | Yes | Yes | No | No
Complex Screen |  | 4 | > 6 | Yes | yes | Yes | Yes | Yes | Yes
| Hybrid | Native iOS | Native Android
Screens
Simple | 4 |  | 8
medium | 8 |  | 16
Complex | 16 |  | 32
0
UI Widgets | Time
Simple | 2 | 2 | 4
Medium | 8 | 8 | 16
Complex | 16 | 16 | 32
0
Native Features |  | 0
Simple | 2 | 2 | 4
Medium | 8 | 8 | 16
Complex | 16 | 16 | 32
0
MultiLingual Support |  | 0
Static Data (For Each Language) | 8 | 8 | 16
|  | 0 | 0
0
Login Requirements |  | 0
Simple Custom Login with Local DB | 8 | 8 | 16
Login With Facebook/Google | 8 | 8 | 16
Integration with LDAP | 40 | 40 | 80
0
Security Requirements |  | 0
SSL | 40 | 40 | 80
Integration with ISAM | 40 | 40 | 80
2-Factor Authentication |  | 0
Custom Data Encryption |  | 0
0
OS Support |  | 0 | 0
Each of the Older versions | 0.2 | 0.2 | 0.4
0
Third Party Integrations |  | 0 | 0
REST Services (for Each Service) | 16 | 16 | 32
SOAP Services (for each service) | 20 | 20 | 40
0
Business logic (Business Rules/Role Based Rules) |  | 0
Simple | 2 | 2 | 4
Medium | 6 | 6 | 12
Complex | 12 | 12 | 24
Analysis & Design Effort | 40%
QA Effort
Analysis | 5%
Test case Creation | 15%
QA Testing | 20%
Total | 40%
Billing Rate
Onsite developer | 160
Offshore Developer | 40
Development Model
Onsite | 20%
Offshore | 80%
Other Effort
Environment Setup | 10%
PM Effort | 15%
Production Support | 5%
Post Production Support | 5%
Buffer | 10%
Security Drop Down Values | 0
1
OS Support Values | 1
2
3
4
|  | % Savings | Total No of Hours | Hours Saved
Assets
| Login Module | 33% | 40 | 13.2
| BlueMix Services integration | 40% | 16 | 6.4
| Push Notification Service | 60% | 12 | 7.2
| IBM Connections App | 40% | 80 | 32
| QR Code Scanner | 50% | 24 | 12
| Basic Hybrid App Functions - Swipe to delete, Pull to refresh | 50% | 16 | 8
| Comments & Ratings | 40% | 24 | 9.6
| File / Photo Upload | 70% | 24 | 16.8
| Payment Gateway integrations | 20% | 20 | 4
| Mobile Analytics - Google, AWS, BlueMix | 20% | 20 | 4
| Build Scripts & Publish | 20% | 28 | 5.6
| Location based services | 50% | 24 | 12
| Chat module | 60% | 30 | 18
| Help text component | 60% | 16 | 9.6
| Tying two ionic components (Tab and Side menu) | 10% | 12 | 1.2
| Key Press Events | 10% | 12 | 1.2
| Menu Gallery | 60% | 24 | 14.4
| Date Picker Gallery | 80% | 12 | 9.6
| Tablet Split View | 80% | 16 | 12.8
| Project Creation plugin | 30% | 20 | 6
Note on A13: Microsoft Office User: Menu Tabs dialog swipe
Note on A14: Microsoft Office User: Menu Tabs dialog swipe
Note on A15: Microsoft Office User: data grid accordion
Note on A18: Microsoft Office User: dialogs splash screen Device orientation Battery Status
Note on A19: Microsoft Office User: inapp browser Acessing contacts media Geolocation Maps Bluetooth On/OFF
Note on A20: Microsoft Office User: File transfer Camera/Scan

## Data
Project Type | App Type | App Framework | UI Framework | Components | Complexity | Backend Technology | Security | Containerization | Analytics | Push Notification | Team Compency | Team Composition | Onsite Effort | Factor | Dev Resource Roles | Resuable assets | % Savings | Total No of Hours | Hours Saved |  | Very Low | Low | Medium | High | Very High |  |  |  |  | Designation | Location | Rate Card
New | Hybrid | AngularJS | Ionic | Plugin Development | Very Low | MobileFirst | Direct Authentication | None | None | None | All Experts | All onshore | 100% | 1 | Developer (onshore) |  |  |  |  | Plugin Development | 4 | 8 | 16 | 40 | 80 | New | 1 | Testing % | 40 | Project Manager | Onsite | 140
Enhancement | Native | Jquery | Choc Chip | Plugin Integration | Low | SAP | SAML | Good | Google Analytics | APN | Mostly Experts | Most onshore | 80% | 1.1 | Developer (offshore) | Login Module | 33% | 40 | 13.2 | Plugin Integration | 4 | 8 | 16 | 40 | 80 | Enhancement | 1.2 | PM % | 20 | Project Manager | Offshore | 40
Rewrite |  | Dojo | Zurb | On-Device Storage | Medium | Parse | TouchID | AirWatch | TeaLeaf | Google Cloud Messenger | Mostly New | Most offshore | 20% | 1.2 | Senior Developer (onshore) | BlueMix Services integration | 40% | 16 | 6.4 | On-Device Storage | 4 | 8 | 16 | 40 | 80 | Rewrite | 0.93 | Architecture % | 20 | Architect | Onsite | 120
Platform Port |  | Other | Other | Security Integration | High | BlueMix | Two-factor | Other | CA | Google and Apple | No Experience | All offshore | 0% | 1.3 | Senior Developer (offshore) | Push Notification Service | 60% | 12 | 7.2 | Security Integration | 4 | 8 | 16 | 40 | 80 | Platform Port | 0.95 | Design % | 20 | Architect | Offshore | 40
|  |  |  | UI - Static | Very High | Other | None |  | Custom | Xtify | [5 empty] | IBM Connections App | 40% | 80 | 32 | UI - Static | 4 | 8 | 16 | 40 | 80 |  |  | Production & Post Production Support % | 2 | UX Designer | Onsite | 120
|  |  |  | UI - Dynamic |  | None |  |  |  | Other | [5 empty] | QR Code Scanner | 50% | 24 | 12 | UI - Dynamic | 4 | 8 | 16 | 40 | 80 |  |  | Testing Support - Developers | 10 | UX Designer | Offshore | 40
|  |  |  | UI - Input | [11 empty] | Basic Hybrid App Functions - Swipe to delete, Pull to refresh | 50% | 16 | 8 | UI - Input | 40 | 80 | 160 | 400 | 800 |  |  | UAT Support - Developers | 5 | UI Developer | Onsite | 120
|  |  |  | App Logic | [11 empty] | Comments & Ratings | 40% | 24 | 9.6 | App Logic | 4 | 8 | 16 | 40 | 80 |  |  | UAT Support - Testers | 5 | UI Developer | Offshore | 40
|  |  |  | Service Consumer | [11 empty] | File / Photo Upload | 70% | 24 | 16.8 | Service Consumer | 4 | 8 | 16 | 40 | 80 |  |  | UAT Testing | 5 | QA Tester | Onsite | 120
|  |  |  | Service Development | [11 empty] | Payment Gateway integrations | 20% | 20 | 4 | Service Development | 4 | 8 | 16 | 40 | 80 |  |  |  |  | QA Tester | Offshore | 40
|  |  |  | Menu | [11 empty] | Mobile Analytics - Google, AWS, BlueMix | 20% | 20 | 4 | Menu | 4 | 8 | 16 | 40 | 80
|  |  |  | GeoLocation/Maps | [11 empty] | Build Scripts & Publish | 20% | 28 | 5.6 | GeoLocation/Maps | 4 | 8 | 16 | 40 | 80
|  |  |  | GeoFencing | [11 empty] | Location based services | 50% | 24 | 12 | GeoFencing | 10 | 20 | 30 | 50 | 60
|  |  |  | Gesture Input | [11 empty] | Chat module | 60% | 30 | 18 | Gesture Input | 4 | 8 | 16 | 40 | 80
|  |  |  | Animation | [11 empty] | Help text component | 60% | 16 | 9.6 | Animation | 4 | 8 | 16 | 40 | 80
|  |  |  | NFC | [11 empty] | Tying two ionic components (Tab and Side menu) | 10% | 12 | 1.2 | NFC | 4 | 8 | 16 | 40 | 80
[16 empty] | Key Press Events | 10% | 12 | 1.2
[16 empty] | Menu Gallery | 60% | 24 | 14.4
[16 empty] | Date Picker Gallery | 80% | 12 | 9.6
[16 empty] | Tablet Split View | 80% | 16 | 12.8
[16 empty] | Project Creation plugin | 30% | 20 | 6