## Summary
PROPOSAL SUMMARY
Client Name | Mattel
Project Name | AG
Total Estimated Effort (hrs) | 261
Effort saved due to Sirius Assets | 36.98%
Total Costs($) | 14379.0367
Cost saved due to Sirius Offshore | 73.76%
Estimated Start Date | 2017-02-01
Estimated End Date | 2017-04-05

## Project Parameters
Client Name | Mattel
Project Name | AG
Category | Detail | Team Competency | Notes | Baseline Effort | Aspect Modifier | Team Modifier | Modified Effort
Project Type | New |  |  |  | 1
Team Composition | Most offshore |  |  |  | 1.2
App Type | Hybrid | Mostly Experts |  | 8 | 1 | 1 | 8
App Framework | Dojo | Mostly Experts |  | 8 | 0.95 | 1 | 7.6
UI Framework | Ionic | All Experts |  | 8 | 1.2 | 0.95 | 9.12
Backend Technology | Parse | Mostly Experts |  | 8 | 1.1 | 1 | 8.8
Security | SAML | Mostly New |  | 8 | 1.2 | 1.2 | 11.52
Containerization |  |  |  | 8 | 1 | 1 | 8
Analytics |  |  |  | 8 | 1 | 1 | 8
Push Notifications |  |  |  | 8 | 1 | 1 | 8
[5 empty] | Baseline Effort |  | 69.04
[5 empty] | Development Effort from Requirements |  | 17.2
[5 empty] | Effort (with Team Composition Overhead) |  | 103.488
[5 empty] | Development Effort - based on Project Type |  | 103.488

## Requirements
Requirement | Requirement Type | Complexity | Reusable Assets | Development Effort | Effort Saved | Total Development Effort: | 17.2
Login | Plugin Development | Low | QR Code Scanner | 4 | 50% | Total Effort Saved | 36.98%
Get Data | App Logic | Very Low | Basic Hybrid App Functions - Swipe to delete, Pull to refresh | 2 | 50%
| Security Integration | Medium | Project Creation plugin | 11.2 | 30%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%
|  |  |  | 0 | 0%

## Effort Estimates
Task | Effort(Hrs)
Architecture Effort | 24.8371
Design Effort | 24.8371
PM Effort | 24.8371
Development Effort - based on Project Type | 103.488
Testing Effort | 49.6742
QA Testing Support - Developers | 12.4186
UAT Testing | 5.1744
UAT Support - Developers | 6.2093
UAT Support - Testers | 6.2093
Production & Post Production Support | 2.4837
Total Estimate | 261
Total Effort Saved in development | 36.98%

## Sprint Calculator (hidden)
Total Effort | 261 | Sprint Durations (in weeks) | 2
|  | Number of Developers | 1
|  | Number of Sprints | 3.2625
PM Resources | 24.8371
Architect Resources | 24.8371
Testing Resources | 49.6742
Creative Resources | 24.8371

## Resource Plan (hidden)
Gantt Chart |  | Elaboration | Construction | Transition
Inception
Elaboration
Construction
Iteration 1
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Transition
Production
Resource Plan |  |  |  |  | Totals
|  | Inception | Inception | Inception
Resource Role |  | 2016-02-01 | 2016-02-08 | 2016-02-15 | Inception | Elaboration | Construction | Transition | Production | Total
BA-CR-UX1 | Business Analyst |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DA1 | Domain Architect |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PM1 | Project Manager |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCDV1 | Developer - Delivery Centre |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCDV2 | Developer - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCUI1 | UI Developer - Onshore - Delivery Centre |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
QAL1 | QA Lead |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSQA1 | Functional Tester - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
INFS1 | Dev Lead - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DD1 | Delivery Executive |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
DCCR1 | Delivery Centre - Coordinator |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSQAL1 | QA Lead - Offshore |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
UX Architect | User Experience Architect |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Creative | Creative Designer |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Infrastructure Specialist |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HOURS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Totals from Resource Plan
Comparison to Estimates |  |  |  |  | Inception | Elaboration | Construction | Transition | Production | Total
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Construction = [Elaboration]+7
Note on C15: Enter project start date

## Cost Estimates
Resources | Onsite Effort(hrs) | Offshore Effort(hrs) | Onsite Cost($) | Offshore Cost($) | Cost if developed at Onsite | Cost Saved due to Offshoring
Architects | 4.9674 | 19.8697 | 596.0909 | 794.7878 | 2980.4544 | 73.33%
Designers | 4.9674 | 19.8697 | 596.0909 | 794.7878 | 2980.4544 | 73.33%
Project Managers | 4.9674 | 19.8697 | 695.4394 | 794.7878 | 3477.1968 | 77.14%
Developers | 20.6976 | 82.7904 | 2483.712 | 3311.616 | 12418.56 | 73.33%
QA testers | 9.9348 | 39.7394 | 1192.1818 | 1589.5757 | 5960.9088 | 73.33%
QA Support - Developers | 2.4837 | 9.9348 | 298.0454 | 397.3939 | 1490.2272 | 73.33%
UAT Support - Developers | 1.2419 | 4.9674 | 149.0227 | 198.697 | 745.1136 | 73.33%
UAT Support - Testers | 1.2419 | 4.9674 | 149.0227 | 198.697 | 745.1136 | 73.33%
Production & Post Production Support | 0.49674 | 1.987 | 59.6091 | 79.4788 | 298.0454 | 73.33%
Total | 50.9989 | 203.9955 | 6219.2148 | 8159.8218 | 31096.0742 | 73.76%
|  | Total Costs | 14379.0367
|  | Cost Saved due to Sirius Offshore | 73.76%
Note on A1: Microsoft Office User: Does'nt include UAT since UAT will be done by Clients

## Plan
RESOURCE PLAN
Total Effort | 261 | hours
Sprint Duration | 4 | weeks
No of developers | 1 | resources
No of testers | 1 | resources
No of UAT Testers | 2 | resources
SPRINT PLAN
Design Schedule | 2 | weeks
Development Schedule | 3 | weeks
Testing Schedule | 2 | weeks
UAT Schedule | 1 | weeks
Production Schedule | 1 | weeks
Total Schedule | 9 | weeks
Total no of sprints | 3 | sprints
SCHEDULE PLAN
Estimated Start Date | 2017-02-01
Estimated End Date | 2017-04-05
EFFORT PLAN
| Week No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
| Week Starting on | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2017-03-01 | 2017-03-08 | 2017-03-15 | 2017-03-22 | 2017-03-29
Architecture & Design Sprint |  | 40 | 9.6742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Sprint |  | 0 | 0 | 40 | 40 | 23.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Testing Sprint |  | 0 | 0 | 0 | 0 | 0 | 40 | 9.6742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Support Sprint |  | 0 | 0 | 0 | 0 | 0 | 6.2093 | 6.2093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Support - Testers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT Support - Developers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production & Post Production Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Data
Project Type | App Type | App Framework | UI Framework | Components | Complexity | Backend Technology | Security | Containerization | Analytics | Push Notification | Team Compency | Team Composition | Onsite Effort | Dev Resource Roles | Resuable assets | % Savings | Total No of Hours | Hours Saved |  | Very Low | Low | Medium | High | Very High |  |  |  |  | Designation | Location | Rate Card
New | Hybrid | AngularJS | Ionic | Plugin Development | Very Low | MobileFirst | Direct Authentication | None | None | None | All Experts | All onshore | 100% | Developer (onshore) |  |  |  |  | Plugin Development | 4 | 8 | 16 | 40 | 80 | New | 1 | Testing % | 40 | Project Manager | Onsite | 140
Enhancement | Native | Jquery | Choc Chip | Plugin Integration | Low | SAP | SAML | Good | Google Analytics | APN | Mostly Experts | Most onshore | 80% | Developer (offshore) | Login Module | 33% | 40 | 13.2 | Plugin Integration | 4 | 8 | 16 | 40 | 80 | Enhancement | 1.2 | PM % | 20 | Project Manager | Offshore | 40
Rewrite |  | Dojo | Zurb | On-Device Storage | Medium | Parse | TouchID | AirWatch | TeaLeaf | Google Cloud Messenger | Mostly New | Most offshore | 20% | Senior Developer (onshore) | BlueMix Services integration | 40% | 16 | 6.4 | On-Device Storage | 4 | 8 | 16 | 40 | 80 | Rewrite | 0.93 | Architecture % | 20 | Architect | Onsite | 120
Platform Port |  | Other | Other | Security Integration | High | BlueMix | Two-factor | Other | CA | Google and Apple | No Experience | All offshore | 0% | Senior Developer (offshore) | Push Notification Service | 60% | 12 | 7.2 | Security Integration | 4 | 8 | 16 | 40 | 80 | Platform Port | 0.95 | Design % | 20 | Architect | Offshore | 40
|  |  |  | UI - Static | Very High | Other | None |  | Custom | Xtify |  |  |  |  | IBM Connections App | 40% | 80 | 32 | UI - Static | 4 | 8 | 16 | 40 | 80 |  |  | Production & Post Production Support % | 2 | UX Designer | Onsite | 120
|  |  |  | UI - Dynamic |  | None |  |  |  | Other |  |  |  |  | QR Code Scanner | 50% | 24 | 12 | UI - Dynamic | 4 | 8 | 16 | 40 | 80 |  |  | Testing Support - Developers | 10 | UX Designer | Offshore | 40
|  |  |  | UI - Input | [10 empty] | Basic Hybrid App Functions - Swipe to delete, Pull to refresh | 50% | 16 | 8 | UI - Input | 40 | 80 | 160 | 400 | 800 |  |  | UAT Support - Developers | 5 | UI Developer | Onsite | 120
|  |  |  | App Logic | [10 empty] | Comments & Ratings | 40% | 24 | 9.6 | App Logic | 4 | 8 | 16 | 40 | 80 |  |  | UAT Support - Testers | 5 | UI Developer | Offshore | 40
|  |  |  | Service Consumer | [10 empty] | File / Photo Upload | 70% | 24 | 16.8 | Service Consumer | 4 | 8 | 16 | 40 | 80 |  |  | UAT Testing | 5 | QA Tester | Onsite | 120
|  |  |  | Service Development | [10 empty] | Payment Gateway integrations | 20% | 20 | 4 | Service Development | 4 | 8 | 16 | 40 | 80 |  |  |  |  | QA Tester | Offshore | 40
|  |  |  | Menu | [10 empty] | Mobile Analytics - Google, AWS, BlueMix | 20% | 20 | 4 | Menu | 4 | 8 | 16 | 40 | 80
|  |  |  | GeoLocation/Maps | [10 empty] | Build Scripts & Publish | 20% | 28 | 5.6 | GeoLocation/Maps | 4 | 8 | 16 | 40 | 80
|  |  |  | GeoFencing | [10 empty] | Location based services | 50% | 24 | 12 | GeoFencing | 10 | 20 | 30 | 50 | 60
|  |  |  | Gesture Input | [10 empty] | Chat module | 60% | 30 | 18 | Gesture Input | 4 | 8 | 16 | 40 | 80
|  |  |  | Animation | [10 empty] | Help text component | 60% | 16 | 9.6 | Animation | 4 | 8 | 16 | 40 | 80
|  |  |  | NFC | [10 empty] | Tying two ionic components (Tab and Side menu) | 10% | 12 | 1.2 | NFC | 4 | 8 | 16 | 40 | 80
[15 empty] | Key Press Events | 10% | 12 | 1.2
[15 empty] | Menu Gallery | 60% | 24 | 14.4
[15 empty] | Date Picker Gallery | 80% | 12 | 9.6
[15 empty] | Tablet Split View | 80% | 16 | 12.8
[15 empty] | Project Creation plugin | 30% | 20 | 6